## Sub Instructions
SUBCONTRACTOR MATERIAL STATUS REPORT - INSTRUCTIONS
All Subcontractors are required to prepare and submit the Material Status Report monthly (at minimum) to the Marous Brothers Construction Project Manager until all materials have been received for the project. All fields in this form must be completed by the Subcontractor per the instructions below. This Subcontractor shall ensure this list includes all materials for a comprehensive report of all items being provided by this Subcontractor. This report will be used by MBC when preparing updated progress schedules and tracking material status throughout the project. As outlined in the Subcontract Agreement: Subcontractors shall prepare a materials status report and shall submit this report as soon as possible, but not later than thirty (30) days after award of the Subcontract Agreement. This form shall be updated on a monthly basis or more often as directed. Delivery dates provided on the materials status report shall conform to the CPM construction schedule. The updated materials status report shall accompany each application for payment.
Trade: |  | Trade or bid package description (ex. Plumbing)
Subcontractor: |  | Subcontractor Company Name
Subcontract Date: |  | Input date of Subcontract Agreement issued by MBC (should match date on executed Subcontract Agreement)
Subs Project Manger: |  | Provide Subcontractor's Project Manager's info including name, mobile phone #, and email address
Subs Foreman: |  | Provide Subcontractor's Foreman or Onsite Supervisor info including name, mobile phone #, and email address
Last Updated Date: |  | Provide last date that information within this form was last updated each time this is submitted to MBC.
Material Item |  | Specific description of material item, a separate line should be provided for each item being purchased by this Subcontractor. If a group of items are coming from one Supplier and will be available at the same time they can be grouped into one line item; however, if there are different lead times for individual components they will need to be listed out as separate items.
Submittals | Submitted Date | Provide the date that the submittal was issued to MBC, this Subcontractor is responsible to make sure submittals are issued promptly allowing for a minimum of 10 days for review and approval by engineer/architect.
| Returned Date | Provide date that the submittal was returned to Subcontractor per Team Viewpoint (The Subcontractor is to review Team Viewpoint to confirm dates that submittals were returned and make sure that submittals noted as pending have not been returned.)
| Submittal Status | Enter submittal status per returned submittal, if the submittal has not been submitted it should be listed as "Not Submitted" and if the submittal has been issued but not yet returned, the status should be listed as "Pending". Submittals noted as revise and resubmit must be addressed and revised submittals to be issued promptly to avoid delays. Any delay resulting from delays in issuing submittals or lost time due to a submittal being returned as revise and resubmit due to items not conforming to the contract documents are this Subcontractor's responsibility.
Material Status | Lead Time (# of Weeks) | Provide the number of weeks required to procure material upon receipt of approved submittals. If a range is provided, the longest potential lead time should be entered based on worst case scenario. This Subcontractor shall verify current lead times with suppliers when completing this form. (If the lead time exceeds the amount of time necessary to ensure materials are onsite, this Subcontractor shall immediately notify the MBC PM and review all options (ex. different suppliers, alternative products, etc.) to expedite and meet project schedule.
| Ordered Date | Provide date that material order was released with Subcontractor, all materials are to be released promptly upon receipt of approved submittals.
| Date Needed On-Site | Provide the date that the material is required onsite per the contract schedule. This Subcontractor must thoroughly review the most current schedule issued by MBC to ensure required delivery dates have not changed. Upon receipt of any updated schedule issued by MBC, this Subcontractor shall review and notify MBC's Project Manager within 2 business days of issuance of the revised schedule in the event that materials may not be available due to revised dates being earlier than the original contract schedule.
| Current Delivery Date | Provide the most current projected delivery date per the supplier. This date must be confirmed with the supplier at the time material is ordered. This Subcontractor must follow-up weekly with suppliers and notify MBC immediately in the event that this delivery date is delayed for any reason.
| Date Last Confirmed | Provide the last date of contact with supplier verifying that material delivery date is still accurate. This Subcontractor must follow-up weekly with suppliers and notify MBC immediately in the event that the projected delivery date has changed for any reason. (A formal letter from the manufacturer must be provided documenting cause of delay for any item that is no longer available by the date required onsite.)
| Material Received (Y/N) | Select "Yes" from the drop down once full quantity of material is delivered onsite or it has been verified that full quantity of material is received at Subcontractor/Suppliers facility and is readily available for delivery to the project. (Material stored off-site must be set aside for this project and not pulled from for other projects prior to delivery) Select "No" if material is still in fabrication or if full quantity has not been received.
| Availability Concern (Y/N) | Select "Yes" from the drop down if the current lead times and confirmed delivery dates do not show material to be onsite to meet the date required or if supplier is not providing projected delivery dates causing concern. (This Subcontractor must include details on concern and what is being done to address the issue in the "Notes / Comment Section for that item if "Yes" is selected. Select "No" if everything is confirmed to be still on track based on most current correspondence.
Supplier Info | Supplier (Company Name) | Provide Supplier's Company Name, Contact Person, Phone Number, and Email for each item. This information is required so that MBC to reach out to Supplier in the event that material delays have occurred or if there is a concern of delay. MBC will include Subcontractor on any email correspondence in regards to these items for this project.
Contact Person
Phone Number
Email
Notes / Comments |  | This area should be used to elaborate on any potential concerns or issues based on the information entered. If there are items that have not been ordered due to field measuring or potential changes discussed with MBC, this should also be noted here. Formal notice must also be issued via email to MBC's Project Manager and Superintendent promptly if Subcontractor becomes aware of potential issues with material delivery dates.

## Sub - Material Status Report
Subcontractor - Material Status Report
This form must be updated monthly by each Subcontractor and issued to MBC Project Manager
| Trade: | [12 empty] | Project:
| Subcontractor: | [12 empty] | Job Number:
Subcontract Date:
| Subs Project Manger: |  |  | Mobile Phone: |  | Email:
| Subs Foreman: |  |  | Mobile Phone: |  | Email: | [7 empty] | Last Updated Date:
|  | Submittals |  |  | Material Status | [6 empty] | Supplier Info
| Material Item | Submitted Date | Returned Date | Submittal Status | Lead Time (# of Weeks) | Ordered Date | Date Needed On-Site | Current Delivery Date | Date Last Confirmed | Material Received (Y/N) | Availability Concern (Y/N) | Supplier (Company Name) | Contact Person | Phone Number | Email | Notes / Comments
230000-001